## Sheet1
Client
Procurement Schedule
|  |  | Item | Description |  |  |  |  | Start Date |  | End Date | February |  |  |  |  | March | [30 empty] | April | [29 empty] | May
[12 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
[12 empty] | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F
Project plan to obtain a fixed price | [11 empty] | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  |  | 0 | Stage 0
| 5.1 |  | 0.1 |  | Briefing of software companies and issue of tender documents |  |  | Mon | 2013-02-25 | bar: Week 1 M 25
|  |  | 0.2 |  | Bidders assemble teams | bar: Week 1 T 26 to Week 1 Th 28
|  |  | 0.3 |  | Notification to Client of Lead Implementer (Prime Contractor) and team composition |  |  | Fri | 2013-03-01 | bar: Week 1 F 1
by NOT later than 16h00 | bar: Week 1 F 1
|  |  | 1 | Stage 1
| 5.2 |  | 1.1 |  | Briefing of lead implementers and teams |  |  | Mon | 2013-03-04 | bar: Week 2 M 4
| 5.3 |  | 1.2 |  | Implementers prepare offers - liaise as required |  |  |  |  | Fri | 2013-03-15 | bar: Week 2 T 5 to Week 3 S 10
|  |  | 1.3 |  | Clarification for bidders |  |  | Mon | 2013-03-11 | bar: Week 3 M 11
two hour Q&A session to enable bidders to obtain clarification all bidders attend
|  |  | 1.4 |  | Implementers finalize offers | bar: Week 3 T 12 to Week 3 F 15
| 5.4 |  | 1.5 |  | Implementers submit offers (5 sets) by not later than 17h00 at Client Offices |  |  | Fri | 2013-03-15 | bar: Week 3 F 15
| 5.5 |  | 1.6 |  | Comparative evaluation of offers -- bidders may be contacted for clarification |  |  | Mon | 2013-03-18 | Weds | 2013-03-20 | bar: Week 4 M 18 to Week 4 W 20
|  | 5.5.4 | 1.7 |  | Bidders advised of outcome -- short list of not more than four bidders |  |  |  |  | Weds | 2013-03-20 | bar: Week 4 W 20
|  |  | 2 | Stage 2
|  |  | 2.1 |  | Four hour site visits (including travelling time) to reference sites |  |  | Mon | 2013-03-25 | Tues | 2013-03-26 | bar: Week 5 M 25 to Week 5 T 26
Bidders will be advised of time slots, drawn by lot, when advised they are on the short list
|  |  | 2.2 |  | Two hour slots per bidder to sit with Client team |  |  | Thurs | 2013-03-28 | bar: Week 5 Th 28
to obtain clarification in order to bring offer to 5% tolerance
Easter weekend | bar: Week 5 F 29 to Week 6 M 1
|  |  | 2.3 |  | Bidders prepare for presentations
|  |  | 2.4 |  | Presentations by Short Listed bidders |  |  | Weds | 2013-04-03 | Thurs | 2013-04-04 | bar: Week 6 T 2 to Week 6 W 3
4 hours including a walkthrough of their software, team and offer and time for questions
Second offer may be lower than first offer as greater clarity is obtained but may NOT exceed
the tolerance of 10% on the initial offer
|  |  | 2.5 |  | Selection of preferred bidder |  |  |  |  | Fri | 2013-04-05 | bar: Week 6 Th 4 to Week 6 F 5
|  |  | 2.6 |  | Notification of bid outcome by Close of Business |  |  |  |  | Fri | 2013-04-05 | bar: Week 6 F 5
|  |  | 3 | Stage 3
| 5.6 |  | 3.1 |  | Finalisation of quote with preferred bidder |  |  | Mon | 2013-04-08 | Thurs | 2013-04-11 | bar: Week 7 M 8 to Week 7 Th 11
Note that final price may NOT exceed the initial offer by more than 10%
and second offer by more than 5%
|  |  | 3.1.1 |  |  | Further discovery in order to finalize price
|  |  | 3.1.2 |  |  | Develop detailed project schedule (Gantt chart)
|  |  | 3.1.3 |  |  | Contractual and commercial negotiations
James Robertson out of town from 12th to 22nd April | bar: Week 7 F 12; Week 8 M 15 to Week 8 F 19; Week 9 M 22
|  |  | 3.2 |  | EXCO review and approval | bar: Week 8 M 15
|  |  | 3.3 |  | Signing of Contract | bar: Week 8 M 15
6 |  |  | 4 | Board approval
7 |  |  | 5 | Commence with system implementation |  |  |  | Mon | 2013-05-06 | bar: Week 11 M 6 to Week 11 F 10; Week 12 M 13 to Week 12 F 17; Week 13 M 20 to Week 13 F 24; Week 14 M 27 to Week 14 Th 30